## TD_Issues
NO | SFRNO | ISSUE_DESCRIPTION | SPC | STATUS | FIXED_DATE | FIXED_UNITS | FIX_DESC | LAST_UPD_DATE | TESTCASENO | CRITICAL
1 | SFR_1 | Maturity Amount is not getting calculated on invoking maturity amount calc Service | Umakant | Open | 2021-02-19
2 | SFR_2 | For unclaimed accounts on maturity date , ictw_acc_prsel population is not happening. also Liquidation entries are not posted to unclaimed GL. [TD0012,TD0013,TD0014] | Vidhya | Open | 2021-03-21
3 | SFR_3 | Deferred Liquidation Date should not exceed Maturity Date | Vidhya | Open | 2021-04-14
4 | SFR_4 | Interest not getting calculated for Backdated Accounts J01000121494 and J01000121483 | Vidhya | Open | 2021-04-14
5 | SFR_5 | Unique Constraint Violation Error during Liquidation/Rollover of Backdated Account Internal Exception: java.sql.SQLIntegrityConstraintViolationException: ORA-00001: unique constraint (FC144ITR.UX01_ICTM_ACC_EFFDT) violated Error Code: 1 Call: INSERT INTO ICTM_ACC_EFFDT (ID, ACC, BRN, ONCE_AUTH, PROD, RECORD_STAT, UDE_EFF_DT) VALUES (?, ?, ?, ?, ?, ?, ?) bind => [7 parameters bound] at org.eclipse.persistence.internal.jpa.EntityManagerImpl.flush(EntityManagerImpl.java:879) at org.eclipse.persistence.internal.jpa.QueryImpl.performPreQueryFlush(QueryImpl.java:972) at org.eclipse.persistence.internal.jpa.QueryImpl.executeUpdate(QueryImpl.java:296) | Vidhya | Open | 2021-04-14

## #PrevIssues
NO | ISSUE_DESCRIPTION | SPC | STATUS | FIXED_DATE | FIXED_UNITS | FIX_DESC | LAST_UPD_DATE | TESTCASENO | CRITICAL
1 | Liquidation not happened for TD account | Vidhya Athmakuri | Fixed | 2020-11-10 | /src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntLiqdProcessImpl.java | commented the deposit flag check in line 1019 | 2020-11-11 |  | Yes
2 | Next_Liq_date coming as null for Ad hoc Liquidation TD maturity case and null pointer exception thrown during table update in IntLiqdRecStoreUtilsImpl.java | Vidhya Athmakuri | Fixed | 2020-11-10 | /src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntLiqdRecStoreUtilsImpl.java | included null check for next_liq_date comparison in line 970. | 2020-11-11 |  | Yes
3 | Since Next_Liq_date is updated as null for TD maturity case, record wont be picked up for maturity processing. TD Specific Code Changes to be added in Liquidation Service. | Vidhya Athmakuri | Fixed | 2020-11-30 | /src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntLiquidationImpl.java | Plsql equivalent code added for calculation of Next_liq_dt and next_schd_liq_dt for deposit case. | 2020-11-30
4 | TD Accounts with Process No 1 is not getting picked for Calc Operation during EOTI | Simulate Again | Hold
5 | When no records are pending for processing in BOD for J01 branch , ICBT in BOD is failing with IC-BAT-105 error | Vidhya Athmakuri | Fixed | 2020-11-17 | /obic-tdbod-alloc-services/src/main/java/oracle/fsgbu/obic/services/tdalloc/batch/TdAllocBatchConfig.java | ACCT and PACT services added to BOD and TD BOD allocation query changed to fetch records until previous date only. | 2020-11-17
6 | Issue with TDUtils.logDepositAccountEvent function 21:19:55:252 ¦ INFO ¦ o.f.o.c.u.TDEventLogUtils ¦ Failed in logDepositAccountEvent() For branchCode ~ custAcNo ~ valueDate ~ eventGM1 ~ GM1000044191 ~ Wed Nov 18 00:00:00 IST 2020 ~ PMAT 21:19:55:252 ¦ ERROR ¦ o.f.o.c.u.TDEventLogUtils ¦ org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'scopedTarget.getApplicationEntityManager': Scope 'request' is not active for the current thread; consider defining a scoped proxy for this bean if you intend to refer to it from a singleton; nested exception is java.lang.IllegalStateException: No thread-bound request found: Are you referring to request attributes outside of an actual web request, or processing a request outside of the originally receiving thread? If you are actually operating within a web request and still receive this message, your code is probably running outside of DispatcherServlet: In this case, use RequestContextListener or RequestContextFilter to expose the current request. | Vidhya Athmakuri | Fixed | 2020-11-16 | /obic-td-bod-services/src/main/java/oracle/fsgbu/obic/services/td/bod/utils/TdBodMiscUtilsImpl.java /obtd-utility/src/main/java/oracle/fsgbu/obtd/common/util/TDEventLogUtils.java /obic-td-bod-services/src/main/java/oracle/fsgbu/obic/services/td/maturity/process/TdMaturityProcessImpl.java | passed EntityManager to the method logDepositAccountEvent. | 2020-11-16
7 | TD Resolution failing with the following error: javax.persistence.PersistenceException: Exception [EclipseLink-6007] (Eclipse Persistence Services - 2.6.7.v20190604-418f1a1c56): org.eclipse.persistence.exceptions.QueryException Exception Description: Missing descriptor for [class java.lang.Number]. Query: ReadAllQuery(referenceClass=Number sql="WITH ttl_months AS ( SELECT (add_months(a.int_start_date, nvl(a.orig_tenor_months, 0) + (nvl(a.orig_tenor_years, 0) * 12)) + nvl(a.orig_tenor_days, 0)) - ADD_MONTHS(a.int_start_date, TRUNC(MONTHS_BETWEEN(add_months(a.int_start_date, nvl(a.orig_tenor_months, 0) + (nvl(a.orig_tenor_years, 0) * 12)) + nvl(a.orig_tenor_days, 0), a.int_start_date))) res, MONTHS_BETWEEN(add_months(a.int_start_date, nvl(a.orig_tenor_months, 0) + (nvl(a.orig_tenor_years, 0) * 12)) + nvl(a.orig_tenor_days, 0), a.int_start_date) mon FROM ictms_acc a WHERE a.acc = p_acc and a.brn = p_brn ) SELECT case when res >= 0 then mon else mon - 0.5 end months FROM ttl_months ") at org.eclipse.persistence.internal.jpa.QueryImpl.getSingleResult(QueryImpl.java:556) | Vidhya Athmakuri | Fixed | 2020-12-28 | obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/dao/ResolveIctmAccRepositoryImpl.java obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/ResolveApplication.java obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/dao/ResolveCftmFloatRateDetailRepositoryImpl.java obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/dao/ResolveTdtbEventDetailsRepositoryImpl.java obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/process/UdeInterestResolution.java obic-interest-resolve-services/oracle/fsgbu/obic/services/intresolve/entities/ResolveTdtbEventDetails.java | Removed Number.class argument from CreateNativeQuery method | 2020-12-28
8 | After TD Authorisation, ictb_maint_queue gets populated with AC Record in U Status but the Processed by is P due to which this will not get picked by Java. | Jeevit | Hold
9 | Dev Environment - TD BOD Service Redeployment is failing. | Vidhya Athmakuri | Fixed | 2020-12-18
10 | 1) PTEOD Batch fails with IC-BAT-102 Error. Test excel Available in Testing_Share\TD_Batch\Testing\SFR9. 2) Though this batch is in failed status, other batches are still getting processed. | Vidhya Athmakuri | Fixed | 2021-01-04
11 | On invoking the TDEOTI Service in Regression, TDMAT and MATY services fails. ROLL Service still remains in O status. (Execcution of Step 10 of Regression) | Vidhya | Closed | 2021-01-13 | /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/entities/IctmAcc.java /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/process/DateChangeProcessor.java /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/process/DateChangeProcessorBatch.java /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/process/DateChangeProcessorImpl.java /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/entities/IctbTdBroken.java /fcubs-co-batch-services/src/main/java/oracle/fsgbu/obic/services/batch/entities/IcvwAccprSel.java
12 | the next liquidation date for accounts - 'J01000121155','J01000101147' is 31-Mar-2020. On 01-Apr-2020 BOD, these accounts are not getting picked for Liquidation. | Vidhya | Closed | 2021-01-16 | /fcubs-td-alloc-services/src/main/java/oracle/fsgbu/obic/services/tdbodalloc/batch/TdBodAllocPartitioner.java /fcubs-td-alloc-services/src/main/java/oracle/fsgbu/obic/services/tdbodalloc/batch/TdBodAllocWriter.java | Modified the for loop incrementer I from 0 to 1
13 | Regression Execution on 01-Apr-2020 is not processing all accruals due to which ICBT remains in W status. | Vidhya | Closed | 2021-01-17 | Related to SFR4
14 | Calc for Account J01000044087 (RD ) fails with error - failed as part of getDetails call from Rule Execution.Error has come after Stage Calling interestSdeOthers for sdeVals branchCode J01 account number J01000044087from date 2020-03-04 to date2020-03-31 AccrFlag true accrDate2020-03-04 sde id DEPOSIT_AMOUNT | Rajamanikam | Closed | 2021-01-19 | NullPointer Exception due to metamodel is null, fixed by adding a namedquery instead of metamodel. | fixed by adding a namedquery instead of metamodel.
15 | ictb_udevals and ictb_udeval_row is not getting populated for any of TD Accounts after SP Resolution. | Jeevit | Closed | 2021-02-09
16 | When maint queue is populated with resolution type AC during EOD, processed by is populated with P. | Jeevit | Fixed | 2021-02-03
17 | tdtb_event_details is not getting updated for TD accounts after liquidation.[J01000121133 and J01000121144] | Rajamanikam | Fixed | 2021-01-15
18 | For TD accounts, the next liquidation date arrived after liquidation is going beyond maturity date of the TD. | Vidhya | Closed | 2021-01-19 | /src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntLiquidationImpl.java | PLSQL Equivalent code added in Liquidation service for Matuirty case
19 | Calc for Account J01000121133 fails with error - failed as part of popSplElems call From Rule Execution.Error has come after Stage Calling interestSdeOthers for sdeVals branchCode J01 account number J01000121133from date 2020-03-04 to date2020-03-31 AccrFlag true accrDate2020-03-04 sde id DEPOSIT_AMOUNT | Vidhya | Fixed | 2021-02-09
20 | Accrual for J01000044189 is not happening. Error message - failed as part of writer layer /failed as part of processor layer in ictb_problem_log. | Vidhya | Fixed | 2021-02-13 | org_service_oper VARCHAR2(50), org_service_param VARCHAR2(4000) columns added to ICTB_INTRADAY_PROD_ENT table.
21 | RD - J01000121133 - Calc is failing with error - failed as part of popSplElems call From Rule Execution.Error has come after Stage Calling interestSdeOthers for sdeVals branchCode J01 account number J01000121133from date 2020-03-04 to date2020-03-31 AccrFlag true accrDate2020-03-04 sde id DAYS_FROM_START | Vidhya | Fixed | 2021-02-13 | Duplicate for SFR7 Calc for Account J01000121133 fails with error - failed as part of popSplElems call From Rule Execution.Error has come after Stage Calling interestSdeOthers for sdeVals branchCode J01 account number J01000121133from date 2020-03-04 to date2020-03-31 AccrFlag true accrDate2020-03-04 sde id DEPOSIT_AMOUNT
22 | TD accounts created on 04-Mar and monthly liquidation. So Liqn date = 31-Mar. On 1st Apr Bod, the accounts will be picked for liquidation. After liquidation, 2 accounts have the entries still in ictb_intraday_acc_control with locked by = N (interest on interest for CASA). [J01000121133 and J01000121144] This table population should not have happened for TD , intonint population logic for TD requires change. | Vidhya | Fixed | 2021-01-18 | /obic-interest-liquidation-services/src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntLiqdRecStoreUtilsImpl.java /obic-interest-liquidation-services/src/main/java/oracle/fsgbu/obic/services/intliqd/process/IntDefrLiqdRecStoreUtilsImpl.java | Changed the multicycle condition to check for nextEventDate +1 < toDate for insertion of record into ictb_intraday_acc_control table for TD Accounts. Search string : TD_MULTICYCLE_FIX
23 | Java AC Resolution for TD Accounts is not updating the next liquidation date, next scheduled liquidation date and deferred liquidation date in ictb_acc_pr for Products with Adhoc Liquidation Frequency. [J01000121268] [Issue still Exists] | Jeevit | Fixed | 2021-02-16 |  |  | 2021-02-09
24 | ictb_udevals and ictb_udeval_row is not getting populated for any of TD Accounts after SP Resolution. Issue reoccurs again. | Jeevit | Fixed | 2021-02-22
25 | When TD Rate Code is given, SP Resolution is not populating the UDE Values correctly. Account Numbers: 'J01000101114','J01000101098','J01000101158' [Issue still exists. ictb_udevals and ictb_udeval_row not getting populated for Spl conditions] | Jeevit | Fixed | 2021-02-03 | UdeInterestResolution.java |  | 2021-02-09
26 | Maturity Date of account J01000101147 is 03-May-2020. While Executing BOD of 03-May,after liquidation following are dates: 1. Next Liq Date - 02-May Last Liq Date = 02-May 2. Next Calc Date - 03-May Last Calc Date = 02-May 3. Next Accr Date - 03-May Last Accr Date = 02-May System Keeps allocating the account for Liquidation and it is going in loop. | Vidhya | Fixed | 2021-02-17
27 | After Liquidation, when tdtb_Event_details is getting populated, topup amount is getting updated with twice of liquidation amount. This is incorrect. Topup amount should get updated only through Topup operation (from screen). | Rajamanikam | Fixed | 2021-02-17
28 | For Rollover Type P + I (Acc: J01000044021 ) following issues are identified: 1. The tenor months and tenor days are updated incorrectly in ictm_td_closure_renew table after rollover. 2. The Amount which has got Rolled over is incorrect. (should include interest also) | Umakant | Closed | 2021-03-15 | \fcubs-td-maturity-services\src\main\java\oracle\fsgbu\fcubs\services\tdmaturity\rollover\process\TdRolloverprocessImpl.java | Tenor days and months were going negative.fix given to correct the positive value
29 | For DCD Account J01000121075, on 01-Apr Bod option status should get updated in ictm_dcd_master.But it is not happening. [Issue still exists] | Vidhya | Closed | 2021-02-15
30 | Special Rollover - Accounting Entires posted is incorrect. Payout entries are missing. | Umakant | Closed | 2021-03-18 | \fcubs-td-maturity-services\src\main\java\oracle\fsgbu\fcubs\services\tdmaturity\rollover\process\TdRolloverProcessImpl.java | Wrong amount was getting passed.
31 | J01000101125 - add funds case - accounting entries for additional pay in amount missing. | Umakant | Closed | 2021-03-18 | \fcubs-td-maturity-services\src\main\java\oracle\fsgbu\fcubs\services\tdmaturity\rollover\process\TdRolloverProcessImpl.java | Query syntax was wrong
32 | tdtb_event_details table is not getting populated after liquidation in Regression Env.(with Postacct changes) | Vidhya | Closed | 2021-03-04
33 | PLIQ - Fails with Null Pointer Exception on inserting IctbIntLiqDetailModel | Vidhya | Closed | 2021-03-16
8 | ictm_td_details.liq_amt not reset to 0 after Rollover | Umakant | Hold | 2021-03-16
7 | Null pointer Exception for 2 threads in Maturity Service since the global parameters comes as null. | Jeevit | Open | 2021-03-16
5 | Interest not getting calculated for Discounted Deposits - J01000044145 and J01000044167 | Vidhya | Closed | 2021-03-30 | /fcubs-tdsde-utils/src/main/java/oracle/fsgbu/tdsde/process/TdSdeIntOthersImpl.java
3 | For RD Account J01000044087 with manual Payment interest amount is not getting calculated. | Vidhya | Closed | 2021-03-30 | /fcubs-tdsde-utils/src/main/java/oracle/fsgbu/tdsde/process/TdSdeIntOthersImpl.java
6 | After Rollover, the data in tdtb_event_details for previous cycle should get deleted after moving to history table. Tdtb_event_details not getting populated correctly after rollover. | Umakant | Closed | 2021-03-29 | fcubs-td-maturity-services\src\main\java\oracle\fsgbu\fcubs\services\tdmaturity\rollover\process\TdRolloverRecStoreUtilsImpl.java
1 | Adhoc holiday changes are not working. Record available in ictb_lcl_affected_hol and ictb_ccy_affected_hol but AHOL is getting updated as Completed though holiday processing didn't happen for branch J01. | Rajamanikam | Closed | 2021-01-27
4 | For RD Account, J01000044076 [TEST030], AutoPayment of RD is not happening on 04-Mar-2020 (Day1 ) ictb_int_liq_details is not getting populated now. | Jeevit | Reject | 2021-04-01 |  | The following two conditions must be satisfied to process RD autopayment. 1) END_OF_INPUT = B or T [Current issue is because END_OF_INPUT = N] 2) Account Balance > RD_AMOUNT
5 | When RD Balance is 0 (Autofunds didn't happen) ,System fails in Calc while trying to get the value for DEPOSIT_AMOUNT SDE with Null Pointer Exception since there is no record in ictb_int_liq_details Table. Debug File Name: CALC_EXCELUSER_J01_BATCH2.2021-03-31.1.log | Vidhya | Closed | 2021-03-31 | /fcubs-tdsde-utils/src/main/java/oracle/fsgbu/tdsde/process/TdSdeIntOthersImpl.java
6 | After Rollover the next maturity date arrived is incorrect when rollover tenor is Account/independent Tenor. | Umakant | Closed | 2021-04-02
7 | tdtb_event_details population after Rollover is incorrect (Balance is wrong and not all records from prev rollover cycles are cleared from this table) | Umakant | Closed | 2021-04-02 | fcubs-td-maturity-services\src\main\java\oracle\fsgbu\fcubs\services\tdmaturity\rollover\process\TdRolloverRecStoreUtilsImpl.java | It was deleting first acc details onlyalways it was going as new this was the reason
4 | Resolution - all accounts are not getting picked for resolution and ictb_job_ctl is not getting cleared. Also not able to see resolution record in intraday_Acc_control during execution. | Jeevit | Closed | 2021-04-09
3 | Post Maturity Process - Records not getting picked from tdtb_maturity_details table for processing. | Vidhya | Closed | 2021-04-01
4 | java.sql.SQLException: ORA-30006: resource busy; acquire with WAIT timeout expired Error during PLIQ operation. Error occurs during invoking Accounting Service for account J01000121155 and record still remains in ictb_intraday_acc_control table after failure (due to locks). Debugs available at: Testing_Share\TD_Batch\Testing\SFR5 | Umakant | Closed | 2021-04-13 | fcubs-td-deposit-services\src\main\java\oracle\fsgbu\obic\services\deposit\pliq\batch\PlqnWriter.java fcubs-td-deposit-services\src\main\java\oracle\fsgbu\obic\services\deposit\pliq\process\PlqnRecStoreUtils.java | Exception handling was not proper .corrected the code for exception handling